## Weekly plan
CI/CD original and revised plan
As of 25 October 2026. Revised plan remains open until cloud evidence is complete.
ID | Week of | Deliverable | Original hours | Revised hours | Status | Acceptance / change
T1 | 2026-10-19T00:00:00.000Z | Requirements and starter inspection | 0.5 | 0.5 | Done | Current rubric captured; original source preserved.
T2 | 2026-10-19T00:00:00.000Z | Validated application and model | 1.5 | 2 | Done | Added schema tests and reproduced matching-version model.
T3 | 2026-10-26T00:00:00.000Z | Cloud Shell clone and make all | 0.5 | 0.5 | To Do | Capture clone, build and separate test screenshots.
T4 | 2026-10-19T00:00:00.000Z | GitHub Actions CI | 0.5 | 0.5 | Done | Run 40173810937 succeeded; 31 tests, lint and artifacts.
T5 | 2026-10-26T00:00:00.000Z | Azure App Service deployment | 0.5 | 0.5 | To Do | Run commands.sh; actual HTTPS prediction and log stream.
T6 | 2026-11-02T00:00:00.000Z | Azure Pipelines automatic delivery | 1 | 1.5 | To Do | Permitted existing connection, test and two deployment runs.
T7 | 2026-11-02T00:00:00.000Z | Trello and final evidence | 0.5 | 0.5 | To Do | Board with To Do / In Progress / Done; genuine screenshots.
T8 | 2026-11-09T00:00:00.000Z | Demo and project handoff | 1 | 1 | To Do | 1080p clear narrated 1–5 minute workflow video.
|  | Total estimated hours | 6 | 7
Source: Current ND082 Building a CI/CD Pipeline rubric, classroom v3.0.16, checked 25 October 2026.
https://learn.udacity.com/nd082?version=3.0.16&partKey=cd1806&lessonKey=63a46e99-9862-4504-b2e4-1b6eabcf1140&project=rubric
Original estimates were preparation targets. Revised estimates include model compatibility and cloud-connection risk.
No actual labour times or completed cloud deployments are inferred from these estimates.
Trello: https://trello.com/b/9wbc68TD/nd082-azure-ci-cd (publicly readable; T1, T2 and T4 Done).
GitHub Actions: https://github.com/djessijorge9-ship-it/nd082-azure-cicd/actions/runs/40173810937

## Annual roadmap
CI/CD annual and quarterly roadmap
Future planning assumptions, not completed work or a commitment to retain training resources.
Period | Goal | Milestone / acceptance | Status
2026 year | Deliver the course application | Working CI/CD, test evidence, plan, video and final review. | In Progress
2026 Q4 | Complete the required workflow | Finish T1–T8; capture genuine cloud results; remove training resources. | In Progress
2027 year | Design maintainable improvements | Production design review and four quarterly improvement milestones. | Future proposal
2027 Q1 | Replace the legacy model dataset | Evaluate a suitable non-discriminatory model and versioned preprocessing. | Future proposal
2027 Q2 | Strengthen release safety | Dependency review, private staging and approved rollback demonstration. | Future proposal
2027 Q3 | Improve operational visibility | Monitor availability and latency; document alert response and recovery. | Future proposal
2027 Q4 | Review cost and supportability | Reassess deployment costs and archive a reproducible release. | Future proposal
Scope: The 2027 roadmap is an optional maintenance proposal. No ongoing Azure spend is authorized.